## Sheet1
Workstream | Milestone | Planned Date | Status | Owner | Dependency
Product Management | Product Charter Approved | 2026-06-01 | Completed | Amanda Chen | None
Product Management | Business Case Approved | 2026-06-05 | Completed | Amanda Chen | Product Charter
Product Management | Launch Budget Approved | 2026-06-12 | Completed | Finance PMO | Business Case
R&D | Product Requirements Baseline | 2026-06-15 | Completed | David Liu | Charter
R&D | Architecture Review Completed | 2026-06-22 | Completed | David Liu | Requirements
R&D | Prototype Build Complete | 2026-07-05 | Completed | Engineering Team | Architecture
R&D | Design Freeze | 2026-08-10 | Completed | David Liu | Prototype
R&D | Firmware Feature Complete | 2026-08-20 | Completed | Firmware Team | Design Freeze
R&D | Security Assessment | 2026-09-10 | On Track | Security Team | Firmware Complete
R&D | Firmware RC2 Build | 2026-09-15 | Completed | Firmware Team | Security Assessment
R&D | Firmware GA | 2026-10-05 | On Track | Firmware Team | RC2
Quality | Validation Test Plan Approved | 2026-08-01 | Completed | Quality Team | Design Freeze
Quality | Reliability Testing | 2026-09-30 | At Risk | Quality Team | Test Plan
Quality | Environmental Test | 2026-09-25 | On Track | QA Lab | Test Plan
Quality | Electromagnetic Test | 2026-09-22 | On Track | QA Lab | Product Build
Quality | Pilot Validation | 2026-10-10 | At Risk | Quality Team | Reliability Test
Quality | Quality Gate Approval | 2026-10-15 | On Track | QA Director | Pilot Validation
Supply Chain | Supplier Identification | 2026-07-10 | Completed | Supply Chain Team | Requirements
Supply Chain | Supplier Qualification | 2026-08-15 | Completed | Procurement Team | Supplier Identification
Supply Chain | Supplier Approval | 2026-09-12 | On Track | Procurement Director | Qualification
Supply Chain | MCU Component Delivery | 2026-09-20 | Blocked | Supplier A | Supplier Approval
Supply Chain | Safety Stock Build | 2026-10-01 | Blocked | Warehouse Team | MCU Delivery
Supply Chain | Regional Inventory Allocation | 2026-10-05 | At Risk | Planning Team | Safety Stock
Manufacturing | Production Line Setup | 2026-08-20 | Completed | Manufacturing Team | Design Freeze
Manufacturing | Pilot Production Run | 2026-09-05 | Completed | Manufacturing Team | Line Setup
Manufacturing | Manufacturing Readiness Review | 2026-09-28 | On Track | Plant Manager | Pilot Run
Manufacturing | Packaging Qualification | 2026-10-02 | On Track | Operations Team | Pilot Run
Manufacturing | First Production Batch | 2026-10-12 | On Track | Plant Manager | Packaging
Marketing | Launch Messaging Review | 2026-09-05 | Completed | Marketing Team | Product Overview
Marketing | Website Content Finalization | 2026-09-25 | On Track | Digital Team | Messaging
Marketing | Launch Campaign Approval | 2026-10-01 | On Track | Marketing Director | Website
Marketing | Analyst Briefing | 2026-10-05 | At Risk | Marketing Director | Campaign Approval
Sales | Sales Kit Development | 2026-09-20 | On Track | Sales Enablement | Product Overview
Sales | Pricing Approval | 2026-09-28 | At Risk | Product Marketing | Sales Kit
Sales | Channel Training Completion | 2026-10-08 | At Risk | Regional Sales Lead | Pricing
Sales | APAC Partner Readiness | 2026-10-12 | On Track | Channel Team | Training
Service | Support Playbook Draft | 2026-09-18 | Completed | Service Team | Product Overview
Service | Knowledge Base Publication | 2026-10-01 | On Track | Support Team | Playbook
Service | L1 Support Training | 2026-10-05 | On Track | Service Training Team | Knowledge Base
Service | Launch Support Readiness | 2026-10-15 | On Track | Service Director | Training
Compliance | China Certification | 2026-09-28 | On Track | Compliance Team | Product Validation
Compliance | Japan Certification | 2026-10-03 | At Risk | Compliance Team | Product Validation
Compliance | Singapore Registration | 2026-10-02 | On Track | Compliance Team | Product Validation
Executive Review | Launch Readiness Review | 2026-10-20 | On Track | Program Manager | All Workstreams
Executive Review | Go / No-Go Decision | 2026-11-01 | On Track | Leadership Team | Readiness Review
Executive Review | APAC Launch Event | 2026-11-15 | On Track | Marketing Director | Go / No-Go