## Sheet1
Risk ID | Category | Risk Description | Impact | Probability | Risk Level | Owner Team | Mitigation Plan | Status
R001 | Supply Chain | MCU核心芯片供应商交期延期2周 | High | High | Critical | Supply Chain | 启用备用供应商并增加空运 | Open
R002 | Supply Chain | 欧洲物流中心库存不足 | Medium | Medium | Medium | Supply Chain | 调整库存调拨计划 | Monitoring
R003 | Supply Chain | 关键电源模块采购成本上涨 | Medium | Medium | Medium | Procurement | 重新议价并锁定价格 | Monitoring
R004 | Manufacturing | 首批量产良率低于95%目标 | High | Medium | High | Manufacturing | 增加试运行批次 | Open
R005 | Quality | 高温可靠性测试失败率高于目标 | High | High | Critical | Quality | 追加可靠性验证与根因分析 | Mitigating
R006 | Quality | EMC测试存在潜在不通过风险 | Medium | Medium | Medium | Quality | 提前安排实验室复测 | Open
R007 | Quality | Pilot Validation结果不稳定 | High | Medium | High | Quality | 延长试点观察周期 | Open
R008 | Engineering | RC3固件功能存在已知缺陷 | Medium | Medium | Medium | R&D | 下一版本修复并重新验证 | Open
R009 | Engineering | Firmware GA版本发布时间延期 | High | Medium | High | R&D | 增加开发资源支持 | Monitoring
R010 | Security | 第三方渗透测试发现高危问题 | High | Low | High | Security | 发布安全补丁 | Open
R011 | Compliance | 日本PSE认证尚未完成 | High | High | Critical | Compliance | 与认证机构加速推进 | Open
R012 | Compliance | 新加坡注册文件等待审批 | Medium | Medium | Medium | Compliance | 跟踪监管审批进度 | Monitoring
R013 | Marketing | 产品官网内容无法按期上线 | Medium | Medium | Medium | Marketing | 启用备用Landing Page | Open
R014 | Marketing | Analyst Briefing时间推迟 | Medium | Medium | Medium | Marketing | 调整媒体沟通计划 | Monitoring
R015 | Sales | APAC渠道培训完成率不足90% | High | High | High | Sales Enablement | 增加在线培训课程 | Open
R016 | Sales | Pricing Approval延期 | High | Medium | High | Product Marketing | 紧急提交审批委员会 | Open
R017 | Sales | 销售团队竞争分析资料缺失 | Medium | Medium | Medium | Sales Operations | 补充竞争分析文档 | Monitoring
R018 | Service | 产品知识库内容不完整 | Medium | Medium | Medium | Customer Service | 增加FAQ及案例内容 | Open
R019 | Service | 一级支持团队培训覆盖率不足 | Medium | Medium | Medium | Customer Service | 增加区域培训场次 | Monitoring
R020 | Executive | 日本市场上市日期是否延期待定 | High | High | Critical | Program Office | 提交管理层决策 | Open